## 项目
|  | 项目名称: |  | 观陵山平台
项目详细
| 开始日期 | 2015-04-09 | 开发者
| 开发时间 |  | 管理者 | 柳哲进
文档记录
No | 日期 | 内容 |  |  | 记录人
1 | 2015-04-09 | 网站和手机端功能进度 |  |  | 尹升日,金学敏
2 | 2015-04-10 | 网站和手机端功能进度修改 |  |  | 柳哲进

## 周期表
项目进度表 |  | 沈阳德铭源科技 damytech @ 2015 | [7 empty] | 0
项目: | 观陵山平台
[6 empty] | 今天: | 2015-04-14 |  |  | Tuesday
(vertical red line)
| 项目管理者: | 柳哲进 | [246 empty] | [42]
| 开始日期: | 2015-04-10 |  | Friday
| 结束日期: | 2015-05-30 |  | Saturday
[42] | [8 empty] | 周一 (星期一:2): | 2 | 2015-04-06 | 2015-04-07 | 2015-04-08 | 2015-04-09 | 2015-04-10 | 2015-04-11 | 2015-04-12 | 2015-04-13 | 2015-04-14 | 2015-04-15 | 2015-04-16 | 2015-04-17 | 2015-04-18 | 2015-04-19 | 2015-04-20 | 2015-04-21 | 2015-04-22 | 2015-04-23 | 2015-04-24 | 2015-04-25 | 2015-04-26 | 2015-04-27 | 2015-04-28 | 2015-04-29 | 2015-04-30 | 2015-05-01 | 2015-05-02 | 2015-05-03 | 2015-05-04 | 2015-05-05 | 2015-05-06 | 2015-05-07 | 2015-05-08 | 2015-05-09 | 2015-05-10 | 2015-05-11 | 2015-05-12 | 2015-05-13 | 2015-05-14 | 2015-05-15 | 2015-05-16 | 2015-05-17 | 2015-05-18 | 2015-05-19 | 2015-05-20 | 2015-05-21 | 2015-05-22 | 2015-05-23 | 2015-05-24 | 2015-05-25 | 2015-05-26 | 2015-05-27 | 2015-05-28 | 2015-05-29 | 2015-05-30 | 2015-05-31 | 2015-06-01 | 2015-06-02 | 2015-06-03 | 2015-06-04 | 2015-06-05 | 2015-06-06 | 2015-06-07 | 2015-06-08 | 2015-06-09 | 2015-06-10 | 2015-06-11 | 2015-06-12 | 2015-06-13 | 2015-06-14 | 2015-06-15 | 2015-06-16 | 2015-06-17 | 2015-06-18 | 2015-06-19 | 2015-06-20 | 2015-06-21 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-27 | 2015-06-28 | 2015-06-29 | 2015-06-30 | 2015-07-01 | 2015-07-02 | 2015-07-03 | 2015-07-04 | 2015-07-05 | 2015-07-06 | 2015-07-07 | 2015-07-08 | 2015-07-09 | 2015-07-10 | 2015-07-11 | 2015-07-12 | 2015-07-13 | 2015-07-14 | 2015-07-15 | 2015-07-16 | 2015-07-17 | 2015-07-18 | 2015-07-19 | 2015-07-20 | 2015-07-21 | 2015-07-22 | 2015-07-23 | 2015-07-24 | 2015-07-25 | 2015-07-26 | 2015-07-27 | 2015-07-28 | 2015-07-29 | 2015-07-30 | 2015-07-31 | 2015-08-01 | 2015-08-02 | 2015-08-03 | 2015-08-04 | 2015-08-05 | 2015-08-06 | 2015-08-07 | 2015-08-08 | 2015-08-09 | 2015-08-10 | 2015-08-11 | 2015-08-12 | 2015-08-13 | 2015-08-14 | 2015-08-15 | 2015-08-16 | 2015-08-17 | 2015-08-18 | 2015-08-19 | 2015-08-20 | 2015-08-21 | 2015-08-22 | 2015-08-23 | 2015-08-24 | 2015-08-25 | 2015-08-26 | 2015-08-27 | 2015-08-28 | 2015-08-29 | 2015-08-30 | 2015-08-31 | 2015-09-01 | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-12 | 2015-09-13 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-19 | 2015-09-20 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-26 | 2015-09-27 | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | 2015-10-10 | 2015-10-11 | 2015-10-12 | 2015-10-13 | 2015-10-14 | 2015-10-15 | 2015-10-16 | 2015-10-17 | 2015-10-18 | 2015-10-19 | 2015-10-20 | 2015-10-21 | 2015-10-22 | 2015-10-23 | 2015-10-24 | 2015-10-25 | 2015-10-26 | 2015-10-27 | 2015-10-28 | 2015-10-29 | 2015-10-30 | 2015-10-31 | 2015-11-01 | 2015-11-02 | 2015-11-03 | 2015-11-04 | 2015-11-05 | 2015-11-06 | 2015-11-07 | 2015-11-08 | 2015-11-09 | 2015-11-10 | 2015-11-11 | 2015-11-12 | 2015-11-13 | 2015-11-14 | 2015-11-15 | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-21 | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27 | 2015-11-28 | 2015-11-29
WBS | 任务 | 开发者 | 开始日期 | 结束日期 | 时间 (天) | % 完成 | 工作时间 | 完成时间 | 剩下日期 | 2: 难度; 2015-04-06: 2015-04-06; 2015-04-13: 2015-04-13; 2015-04-20: 2015-04-20; 2015-04-27: 2015-04-27; 2015-05-04: 2015-05-04; 2015-05-11: 2015-05-11; 2015-05-18: 2015-05-18; 2015-05-25: 2015-05-25; 2015-06-01: 2015-06-01; 2015-06-08: 2015-06-08; 2015-06-15: 2015-06-15; 2015-06-22: 2015-06-22; 2015-06-29: 2015-06-29; 2015-07-06: 2015-07-06; 2015-07-13: 2015-07-13; 2015-07-20: 2015-07-20; 2015-07-27: 2015-07-27; 2015-08-03: 2015-08-03; 2015-08-10: 2015-08-10; 2015-08-17: 2015-08-17; 2015-08-24: 2015-08-24; 2015-08-31: 2015-08-31; 2015-09-07: 2015-09-07; 2015-09-14: 2015-09-14; 2015-09-21: 2015-09-21; 2015-09-28: 2015-09-28; 2015-10-05: 2015-10-05; 2015-10-12: 2015-10-12; 2015-10-19: 2015-10-19; 2015-10-26: 2015-10-26; 2015-11-02: 2015-11-02; 2015-11-09: 2015-11-09; 2015-11-16: 2015-11-16; 2015-11-23: 2015-11-23
1 | 原型图确定及制作 | 尹升日,张忠昱 | 2015-04-09 | 2015-04-14 | 6 | 100% | 4 | 6 | 0 | 2: 100
1.1 | 访客 |  | 2015-04-09 | 2015-04-09 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.1.1 | 园区介绍 |  | 2015-04-09 | 2015-04-09 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.1.2 | 殡葬知识 |  | 2015-04-09 | 2015-04-09 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.1.3 | 生活小知识 |  | 2015-04-09 | 2015-04-09 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.1.4 | 小游戏 |  | 2015-04-09 | 2015-04-09 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2 | 旧客户 |  | 2015-04-10 | 2015-04-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2.1 | 园区活动通知 |  | 2015-04-10 | 2015-04-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2.2 | 亲人生殁日通知 |  | 2015-04-10 | 2015-04-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2.3 | 亲人数据查询 |  | 2015-04-10 | 2015-04-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2.4 | 落葬仪式预约 |  | 2015-04-10 | 2015-04-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2.5 | 在线活动祭品购买 |  | 2015-04-10 | 2015-04-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2.6 | 代祭拜回函 |  | 2015-04-10 | 2015-04-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.2.7 | 服务人员资料 |  | 2015-04-10 | 2015-04-10 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.3 | 代销商 |  | 2015-04-11 | 2015-04-11 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.3.1 | 园区活动 业务制度通知 |  | 2015-04-11 | 2015-04-11 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.3.2 | 在线保留系统 |  | 2015-04-11 | 2015-04-11 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.3.3 | 在线代订活动祭品 |  | 2015-04-11 | 2015-04-11 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.3.4 | 在线商品奖金计算 |  | 2015-04-11 | 2015-04-11 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.3.5 | 在线祭品奖金计算 |  | 2015-04-11 | 2015-04-11 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.3.6 | 落葬仪式预约 |  | 2015-04-11 | 2015-04-11 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.3.7 | 观陵山服务人员资料 |  | 2015-04-11 | 2015-04-11 | 1 | 100% | 0 | 1 | 0 | 2: 100
1.4 | 员工 |  | 2015-04-13 | 2015-04-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.4.1 | 园区活动业务制度通知 |  | 2015-04-13 | 2015-04-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.4.2 | 在线保留系统 |  | 2015-04-13 | 2015-04-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.4.3 | 在线陵园订购 |  | 2015-04-13 | 2015-04-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.4.4 | 在线代订活动祭品 |  | 2015-04-13 | 2015-04-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.4.5 | 在线商品奖金计算 |  | 2015-04-13 | 2015-04-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.4.6 | 代销人员资料 |  | 2015-04-13 | 2015-04-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.4.7 | 落葬仪式预约 |  | 2015-04-13 | 2015-04-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.4.8 | 自有客户商品订购通知 |  | 2015-04-13 | 2015-04-13 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5 | 领导 |  | 2015-04-14 | 2015-04-14 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5.1 | 出勤内容 |  | 2015-04-14 | 2015-04-14 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5.2 | 每月各办事处单月业绩 |  | 2015-04-14 | 2015-04-14 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5.3 | 每年累进业绩 |  | 2015-04-14 | 2015-04-14 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5.4 | 单日业绩 |  | 2015-04-14 | 2015-04-14 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5.5 | 单日落葬人数 |  | 2015-04-14 | 2015-04-14 | 1 | 100% | 1 | 1 | 0 | 2: 100
1.5.6 | 代销人员业绩 |  | 2015-04-14 | 2015-04-14 | 1 | 100% | 1 | 1 | 0 | 2: 100
2 | Android开发 | 全部 | 2015-04-10 | 2015-05-19 | 40 |  | 28 | 0 | 40 | 2: 100
2.1 | Demo开发 |  | 2015-04-10 | 2015-04-25 | 16 | #DIV/0! | 11 | #DIV/0! | #DIV/0! | 2: 100
2.1.1 | 访客 |  | 2015-04-10 | 2015-04-14 | 5 | 95% | 3 | 4 | 1 | 2: 100
2.1.1.1 | 园区介绍 | 金玉哲,金学敏 | 2015-04-10 | 2015-04-14 | 5 | 100% | 3 | 5 | 0 | 2: 100
2.1.1.2 | 殡葬知识 | 李哲 | 2015-04-10 | 2015-04-11 | 2 | 100% | 1 | 2 | 0 | 2: 300
2.1.1.3 | 生活小知识 | 李哲 | 2015-04-12 | 2015-04-14 | 3 | 80% | 2 | 2 | 1 | 2: 100
2.1.1.4 | 小游戏 | 肖娜娜 | 2015-04-10 | 2015-04-11 | 2 | 100% | 1 | 2 | 0 | 2: 100
2.1.2 | 旧客户 | 金玉哲,李哲,金学敏 | 2015-04-12 | 2015-04-21 | 10 | #DIV/0! | 7 | #DIV/0! | #DIV/0! | 2: 100
2.1.2.1 | 园区活动通知 |  |  |  |  | 0% | 0 | 0 | 0 | 2: 100
2.1.2.2 | 亲人生殁日通知 |  |  |  |  | 0% | 0 | 0 | 0 | 2: 100
2.1.2.3 | 亲人数据查询 |  |  |  |  | 0% | 0 | 0 | 0 | 2: 100
2.1.2.4 | 落葬仪式预约 |  |  |  |  | 0% | 0 | 0 | 0 | 2: 100
2.1.2.5 | 在线活动祭品购买 |  |  |  |  | 0% | 0 | 0 | 0 | 2: 100
2.1.2.6 | 代祭拜回函 |  |  |  |  | 0% | 0 | 0 | 0 | 2: 100
2.1.2.7 | 服务人员资料 |  |  |  |  | 0% | 0 | 0 | 0 | 2: 100
2.1.3 | 代销商 | 金玉哲,李哲,金学敏 | 2015-04-22 | 2015-04-26 | 5 |  | 3 | 0 | 5 | 2: 100
2.1.3.1 | 园区活动 业务制度通知 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.3.2 | 在线保留系统 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.3.3 | 在线代订活动祭品 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.3.4 | 在线商品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.3.5 | 在线祭品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.3.6 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.3.7 | 观陵山服务人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.4 | 员工 | 金玉哲,李哲,金学敏 | 2015-04-22 | 2015-04-26 | 5 |  | 3 | 0 | 5 | 2: 100
2.1.4.1 | 园区活动业务制度通知 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.4.2 | 在线保留系统 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.4.3 | 在线陵园订购 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.4.4 | 在线代订活动祭品 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.4.5 | 在线商品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.4.6 | 代销人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.4.7 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.4.8 | 自有客户商品订购通知 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.5 | 领导 | 金学敏 | 2015-04-22 | 2015-04-26 | 5 |  | 3 | 0 | 5 | 2: 100
2.1.5.1 | 出勤内容 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.5.2 | 每月各办事处单月业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.5.3 | 每年累进业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.5.4 | 单日业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.5.5 | 单日落葬人数 | [5 empty] | 0 | 0 | 0 | 2: 100
2.1.5.6 | 代销人员业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2 | 开发完成 | 肖娜娜 | 2015-04-26 | 2015-05-18 | 23 |  | 16 | 0 | 23 | 2: 100
2.2.1 | 访客 |  | 2015-04-26 | 2015-04-27 | 2 |  | 1 | 0 | 2 | 2: 100
2.2.1.1 | 首页界面 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.1.2 | 园区介绍 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.1.3 | 殡葬知识 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.1.4 | 生活小知识 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.1.5 | 小游戏 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.2 | 旧客户 |  | 2015-04-28 | 2015-04-29 | 2 |  | 2 | 0 | 2 | 2: 100
2.2.2.1 | 园区活动通知 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.2.2 | 亲人生殁日通知 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.2.3 | 亲人数据查询 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.2.4 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.2.5 | 在线活动祭品购买 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.2.6 | 代祭拜回函 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.2.7 | 服务人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.3 | 代销商 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.3.1 | 园区活动 业务制度通知 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.3.2 | 在线保留系统 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.3.3 | 在线代订活动祭品 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.3.4 | 在线商品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.3.5 | 在线祭品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.3.6 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.3.7 | 观陵山服务人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.4 | 员工 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.4.1 | 园区活动业务制度通知 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.4.2 | 在线保留系统 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.4.3 | 在线陵园订购 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.4.4 | 在线代订活动祭品 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.4.5 | 在线商品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.4.6 | 代销人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.4.7 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.4.8 | 自有客户商品订购通知 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.5 | 领导 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.5.1 | 出勤内容 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.5.2 | 每月各办事处单月业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.5.3 | 每年累进业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.5.4 | 单日业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.5.5 | 单日落葬人数 | [5 empty] | 0 | 0 | 0 | 2: 100
2.2.5.6 | 代销人员业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
3 | iPhone开发 | 李哲，尹升日 |  |  |  |  | 0 | 0 | 0 | 2: 100
3.1 | 访客 | [5 empty] | 0 | 0 | 0 | 2: 100
3.1.1 | 园区介绍 | [5 empty] | 0 | 0 | 0 | 2: 100
3.1.2 | 殡葬知识 | [5 empty] | 0 | 0 | 0 | 2: 100
3.1.3 | 生活小知识 | [5 empty] | 0 | 0 | 0 | 2: 100
3.1.4 | 小游戏 | [5 empty] | 0 | 0 | 0 | 2: 100
3.2 | 旧客户 | [5 empty] | 0 | 0 | 0 | 2: 100
3.2.1 | 园区活动通知 | [5 empty] | 0 | 0 | 0 | 2: 100
3.2.2 | 亲人生殁日通知 | [5 empty] | 0 | 0 | 0 | 2: 100
3.2.3 | 亲人数据查询 | [5 empty] | 0 | 0 | 0 | 2: 100
3.2.4 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
3.2.5 | 在线活动祭品购买 | [5 empty] | 0 | 0 | 0 | 2: 100
3.2.6 | 代祭拜回函 | [5 empty] | 0 | 0 | 0 | 2: 100
3.2.7 | 服务人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
3.3 | 代销商 | [5 empty] | 0 | 0 | 0 | 2: 100
3.3.1 | 园区活动 业务制度通知 | [5 empty] | 0 | 0 | 0 | 2: 100
3.3.2 | 在线保留系统 | [5 empty] | 0 | 0 | 0 | 2: 100
3.3.3 | 在线代订活动祭品 | [5 empty] | 0 | 0 | 0 | 2: 100
3.3.4 | 在线商品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
3.3.5 | 在线祭品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
3.3.6 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
3.3.7 | 观陵山服务人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
3.4 | 员工 | [5 empty] | 0 | 0 | 0 | 2: 100
3.4.1 | 园区活动业务制度通知 | [5 empty] | 0 | 0 | 0 | 2: 100
3.4.2 | 在线保留系统 | [5 empty] | 0 | 0 | 0 | 2: 100
3.4.3 | 在线陵园订购 | [5 empty] | 0 | 0 | 0 | 2: 100
3.4.4 | 在线代订活动祭品 | [5 empty] | 0 | 0 | 0 | 2: 100
3.4.5 | 在线商品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
3.4.6 | 代销人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
3.4.7 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
3.4.8 | 自有客户商品订购通知 | [5 empty] | 0 | 0 | 0 | 2: 100
3.5 | 领导 | [5 empty] | 0 | 0 | 0 | 2: 100
3.5.1 | 出勤内容 | [5 empty] | 0 | 0 | 0 | 2: 100
3.5.2 | 每月各办事处单月业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
3.5.3 | 每年累进业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
3.5.4 | 单日业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
3.5.5 | 单日落葬人数 | [5 empty] | 0 | 0 | 0 | 2: 100
3.5.6 | 代销人员业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
4 | 数据库设计 | 尹升日 | 2015-04-18 | 2015-04-21 | 4 |  | 2 | 0 | 4 | 2: 100
4.1 | 用户管理 | [5 empty] | 0 | 0 | 0 | 2: 100
4.2 | 地图管理 | [5 empty] | 0 | 0 | 0 | 2: 100
4.3 | 生活知识管理 | [5 empty] | 0 | 0 | 0 | 2: 100
4.4 | 商品管理 | [5 empty] | 0 | 0 | 0 | 2: 100
4.5 | 预约管理 | [5 empty] | 0 | 0 | 0 | 2: 100
4.6 | 订购管理 | [5 empty] | 0 | 0 | 0 | 2: 100
4.7 | 通知管理 | [5 empty] | 0 | 0 | 0 | 2: 100
4.8 | 出勤管理 | [5 empty] | 0 | 0 | 0 | 2: 100
4.9 | 业绩管理 | [5 empty] | 0 | 0 | 0 | 2: 100
5 | Web Service开发 | 金学敏,尹升日 | 2015-04-22 | 2015-05-21 | 30 |  | 22 | 0 | 30 | 2: 100
5.1 | 访客 |  | 2015-04-22 | 2015-04-24 | 3 |  | 3 | 0 | 3 | 2: 100
5.1.1 | 园区介绍 | [5 empty] | 0 | 0 | 0 | 2: 100
5.1.2 | 殡葬知识 | [5 empty] | 0 | 0 | 0 | 2: 100
5.1.3 | 生活小知识 | [5 empty] | 0 | 0 | 0 | 2: 100
5.1.4 | 小游戏 | [5 empty] | 0 | 0 | 0 | 2: 100
5.2 | 旧客户 |  | 2015-04-26 | 2015-05-21 | 26 |  | 19 | 0 | 26 | 2: 100
5.2.1 | 园区活动通知 | [5 empty] | 0 | 0 | 0 | 2: 100
5.2.2 | 亲人生殁日通知 | [5 empty] | 0 | 0 | 0 | 2: 100
5.2.3 | 亲人数据查询 | [5 empty] | 0 | 0 | 0 | 2: 100
5.2.4 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
5.2.5 | 在线活动祭品购买 | [5 empty] | 0 | 0 | 0 | 2: 100
5.2.6 | 代祭拜回函 | [5 empty] | 0 | 0 | 0 | 2: 100
5.2.7 | 服务人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
5.3 | 代销商 |  | 2015-04-26 | 2015-05-21 | 26 |  | 19 | 0 | 26 | 2: 100
5.3.1 | 园区活动 业务制度通知 | [5 empty] | 0 | 0 | 0 | 2: 100
5.3.2 | 在线保留系统 | [5 empty] | 0 | 0 | 0 | 2: 100
5.3.3 | 在线代订活动祭品 | [5 empty] | 0 | 0 | 0 | 2: 100
5.3.4 | 在线商品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
5.3.5 | 在线祭品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
5.3.6 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
5.3.7 | 观陵山服务人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
5.4 | 员工 |  | 2015-04-26 | 2015-05-21 | 26 |  | 19 | 0 | 26 | 2: 100
5.4.1 | 园区活动业务制度通知 | [5 empty] | 0 | 0 | 0 | 2: 100
5.4.2 | 在线保留系统 | [5 empty] | 0 | 0 | 0 | 2: 100
5.4.3 | 在线陵园订购 | [5 empty] | 0 | 0 | 0 | 2: 100
5.4.4 | 在线代订活动祭品 | [5 empty] | 0 | 0 | 0 | 2: 100
5.4.5 | 在线商品奖金计算 | [5 empty] | 0 | 0 | 0 | 2: 100
5.4.6 | 代销人员资料 | [5 empty] | 0 | 0 | 0 | 2: 100
5.4.7 | 落葬仪式预约 | [5 empty] | 0 | 0 | 0 | 2: 100
5.4.8 | 自有客户商品订购通知 | [5 empty] | 0 | 0 | 0 | 2: 100
5.5 | 领导 |  | 2015-04-26 | 2015-05-21 | 26 |  | 19 | 0 | 26 | 2: 100
5.5.1 | 出勤内容 | [5 empty] | 0 | 0 | 0 | 2: 100
5.5.2 | 每月各办事处单月业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
5.5.3 | 每年累进业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
5.5.4 | 单日业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
5.5.5 | 单日落葬人数 | [5 empty] | 0 | 0 | 0 | 2: 100
5.5.6 | 代销人员业绩 | [5 empty] | 0 | 0 | 0 | 2: 100
6 | 后台网站开发 | 网站开发组 | 2015-04-16 |  |  |  | -30079 | 0 | 0 | 2: 100
6.1 | 园区信息 | 史瑞丰 | 2015-04-16 | 2015-05-10 | 25 |  | 17 | 0 | 25 | 2: 100
6.1.1 | 一条龙服务（有排序功能） |  |  |  | 3 |  | 0 | 0 | 3 | 2: 100
6.1.2 | 园区服务管理（落葬服务+代祭拜服务+祭品订购） |  |  |  | 3 |  | 0 | 0 | 3 | 2: 100
6.1.3 | 园区墓地商品管理+墓地预定 |  |  |  | 3 |  | 0 | 0 | 3 | 2: 100
6.1.4 | 园区祭拜用品管理 |  |  |  | 3 |  | 0 | 0 | 3 | 2: 100
6.1.5 | 办事处管理 |  |  |  | 3 |  | 0 | 0 | 3 | 2: 100
6.1.6 | 百度地图上添加办事处地址 |  |  |  | 3 |  | 0 | 0 | 3 | 2: 100
6.1.7 | 园区活动通知(发布新通知推送到手机) |  |  |  | 3 |  |  | 0 | 3
6.1.8 | 园区活动（原36景） |  |  |  | 2 |  | 0 | 0 | 2 | 2: 100
6.1.9 | 园区信息修改(公司简介+购墓流程+购墓注意事项+落葬习俗+殡葬新闻) |  |  |  | 2 |  | 0 | 0 | 2 | 2: 100
6.2 | 预约管理 | 刘俊宏 | 2015-04-20 | 2015-05-07 | 18 | #VALUE! | 758358 | -716227 | 100
6.2.1 | 参观预约管理+导出 |  |  |  | 4 | 0 | 0 | 0 | 100
6.2.2 | 落葬仪式预约+导出 |  |  |  | 4 |  | 0 | 0 | 4 | 2: 100
6.2.3 | 祭拜预约+导出 |  |  |  | 4
6.2.4 | 代寄拜回函发送 |  |  |  | 4
6.2.5 | 单位时间预约人数设置 |  |  |  | 2
6.3 | 系统用户管理 | 张忠昱，刘俊宏 | 2015-04-16 |  |  |  | -30079 | 0 | 0 | 2: 100
6.3.1 | 休假管理 | 刘俊宏 | 2015-04-16 | 2015-04-19 | 4 |  | 2 | 0 | 4 | 2: 100
6.3.2 | 用户管理 | 张忠昱 | 2015-04-20 | 2015-04-29 | 10 |  | 8 | 0 | 10 | 2: 100
6.3.2.1 | 旧客户 |  |  |  | 2 |  | 0 | 0 | 2 | 2: 100
6.3.2.2 | 员工 |  |  |  | 2 |  | 0 | 0 | 2 | 2: 100
6.3.2.3 | 代销商 |  |  |  | 2 |  | 0 | 0 | 2 | 2: 100
6.3.2.4 | 领导 |  |  |  | 2 |  |  | 0 | 2
6.3.2.5 | 系统使用用户 |  |  |  | 2 |  |  | 0 | 2
6.4 | 订单管理 | 刘俊宏 | 2015-05-08 | 2015-05-24 | 17 |  | 11 | 0 | 17 | 2: 100
6.4.1 | 陵墓订单+导出（包含保留） |  |  |  | 7 |  | 0 | 0 | 7 | 2: 100
6.4.2 | 祭拜用品订单+导出 |  |  |  | 7 |  | 0 | 0 | 7 | 2: 100
6.4.3 | 修改订单备注 |  |  |  | 3
6.5 | 业绩管理 | 史瑞丰 | 2015-05-11 | 2015-05-28 | 18 |  | 14 | 0 | 18 | 2: 100
6.5.1 | 查看员工/代销商/办事处业绩+导出 |  |  |  | 10 |  | 0 | 0 | 10 | 2: 100
6.5.2 | 添加业绩 |  |  |  | 5
6.5.3 | 推送到手机 |  |  |  | 3 |  | 0 | 0 | 3 | 2: 100
6.6 | 其他 | 肖娜娜 | 2015-04-16 | 2015-05-03 | 18 |  | 12 | 0 | 18 | 2: 100
6.6.1 | 旅游景点管理（导航功能） |  |  |  | 2 |  |  | 0 | 2
6.6.2 | 衣食住行管理（链接地址，育为上传图片） |  |  |  | 2 |  | 0 | 0 | 2 | 2: 100
6.6.3 | 游戏管理（链接地址） |  |  |  | 2 |  | 0 | 0 | 2 | 2: 100
6.6.4 | 奖金计算公式调整 |  |  |  | 2 |  | 0 | 0 | 2 | 2: 100
6.6.5 | 责任额度管理 |  |  |  | 2
6.6.6 | 地区管理 |  |  |  | 2 |  | 0 | 0 | 2 | 2: 100
6.6.7 | 修改密码 |  |  |  | 2 |  |  | 0 | 2
6.6.8 | 墓地预留时间调整 |  |  |  | 2 |  |  | 0 | 2
6.6.9 | 落葬场次人数调整 |  |  |  | 2 |  |  | 0 | 2
6.6.10 | 定金金额与时间调整

## 预算
Budget
Project |  | Project #
Project manager |  | Sponsor | 0
Project artifacts |  | Updated
Budget Status
Approved Budget | Planned Expenditures to Date | Actual Expenditures to Date | Variance
0 | 0 | 0 | 0
| Planned Remaining Budget | Actual Remaining Budget | Variance
| 0 | 0 | 0
Additional $ needed
Budget Details
Internal Expenses
Salaries | Hourly Rate | # Hours | Total Cost
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Type of resource | 0 | 0 | 0
Other Internal Expenses |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total Internal Expenses |  |  |  | 0
External Expenses
Consulting Costs |  |  | Total Cost
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Type of consulting |  |  | 0
Capital Expenditures |  |  | Total Cost
Type of expense |  |  | 0
Type of expense |  |  | 0
Type of expense |  |  | 0
Total External Expenses |  |  |  | 0
Total Budget |  |  |  | 0

## 风险登记
风险管理 (风险登记)
Project | [8 empty] | Project #
Project manager | [8 empty] | Sponsor | 0
Project artifacts | [8 empty] | Updated
ID | Risk Description | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Contingency Plan | Owner | Status | Date Entered | Date to Review
1 | What is this risk? | 1 | 2 | 3 | 12 |  | What act or event initiates either the risk occurrence or precipitates the response strategy? | How will you respond to this risk and what actions will you take to match that response? | If the risk becomes a reality, what will you do in response, as a backup, or alternative/ workaround? | Who monitors this risk?
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0

## 问题日志
问题日志
Project |  |  |  | Project #
Project manager |  |  |  | Sponsor | 0
Project artifacts |  |  |  | Updated
ID | Issue Description | Project Impact | Action Plan/Resolution | Owner | Importance | Date Entered | Date to Review | Date Resolved
1 | What is the issue? | How will this impact scope, schedule & cost? | How do you intend to deal with this issue? | Who manages this issue?
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## © (hidden)
Gantt Chart Template
© 2008-2009 Vertex42 LLC
http://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html